## Required Information
| Required Information before starting code | Comments
1 | Provide functional walk-through (Screen wise and Business of each screen) before start the development | Scheduled Walk through session with Jill on 07/19 @ 10:00 AM EST
2 | Required help on Environment setup | Code path and Database details shared below
3 | Database information with credentials | Development: TECH10 QA: TECH_QA PRODUCTION: TECHNICAL Schemas / Password: ICS/COOPERTIRE and ICS_PROCS/1234, these credentials are for DEVL database. As part of upgradation these objects needs to be moved to new database
4 | TFS/Source Location Path for Latest code base | Currently application is in $/Serena/Dev/ICS need to be move it under "Corporate Quality Systems" Current application version is VS2005
5 | Any existing documentation available for functional flow and also test cases | Jill is going to look for some documents and share those accordingly
6 | Any existing test cases for ICS | No
7 | What are the AD groups and roles for this application | APP_ICS_MKT, APP_ICS_QS_EMP, APP_ICS_QS_MGR, APP_ICS_QUEREY Need to check with Jill during KT Session on what role we should be to test the application
8 | Any special jobs running for processing data for this application? | ICS_PROCS.UNLOAD_CERTIFICATEACTIVITY this job places flat file to shared path \\FA0017\ICS\OUT\ We can ask more details in the session, like is this is the only job, is the path common for all environments
9 | Any special precaution need to take care for this application? | We can ask during KT session
10 | Any integration with other applications? | We can ask during KT session
11 | How many users are accessing this application | We can ask during KT session
12 | List of pre-existing Issues | We can ask during KT session
13 | Provide the current running application URL to access the offshore | Production: http://cooperwebfinprod/scit/applications/ICSWeb/home.aspx QA: http://cooperwebfinqa/scit/applications/ICSWeb/home.aspx Development: http://cooperwebfindev/scit/applications/ICSWeb/home.aspx Currently DEV URL is not working, request has been putin to look for it
Note | As part of the this application we are standardizing the code and implementing Coding Standards for Existing Code No Functional Changes in scope.
Any existing issues are not in scope

## Activities
Activities
1 | Environment setup
2 | Upgrade to vs2013
3 | Implement sandcastle comments
4 | .Net code standardization
5 | Parameter validations
6 | Localization | Creating resource files
7 | Any minimal changes in crystal reports
8 | DB Code standardization