## Form Instructions (hidden)
Business Case (DRAFT Rev. 18, 05/02/2018) Form Instructions
1.0 | General Instructions
1.1 | The Business Case is an integral part of the project prioritization process for BIS. The information in the Business Case will be used to prioritize projects according to pre-determined criteria and weighting. It is imperative that all information in the Business Case is collected. ANY ASSUMPTIONS MADE AS PART OF COMPLETING THE BUSINESS CASE SHOULD BE NOTED ON THE ASSUMPTIONS SHEET OF THIS SPREADSHEET. to fill out the business case, use the drop down lists to pick the appropriate values.
| Cells that are colored light yellow: |  |  | need to be completed as part of the Business Case and BIS Assessment.
1.2 | Definitions
| 1.2.1 | Alignment with the Strategic Plan
Project alignment with the Strategic Goals: Consider a) Drive topline profitable growth - Americas and International b) Develop a competitive cost structure and improve profitability c) Build organizational capabilities. These are items that are fully aligned with the 6x12x20 and a potential project should focus on at least one. Alignment to the 6x12x20 is measured under the "Strategic Project" category.
| 1.2.2 | BIS Assessment
This is a worksheet that can be used to help estimate the BIS hours of effort and the cost to realize the project results.
| 1.2.3 | Continuous Improvement
Continuous Improvement is a culture that is supported by project work that improves the day-to-day operations of Cooper Tire. Processes that are identified as broke and not working and do not provide the value to Cooper needs to be improved to a higher performance level. Without a continuous improvement effort: 1) A broke or inefficient process will continue to falter and fail to provide value to the organization, i.e. decreasing departmental efficiency and increasing waste or 2) Process improvements leading to increased revenues through cost savings or improvement sin process efficiency will not be realized.
| 1.2.4 | Existing / Legacy Technology or Functionality Enhancements
This is an enhancement to technology or functionality that is existing at Cooper. Nothing new needs to be added, just modification to something existing.
| 1.2.5 | Government Mandated
A project is needed to deliver a result, service or product that is required to comply with federal or state regulations by a specific deadline given by the federal or state agency. This could also be a foreign government mandate that is required to sell products in that government's country. There could be a penalty or fine and the risk of non-compliance has been assessed and is known.
| 1.2.6 | Industry Mandated
The project is required to meet specific standard within the industry to be able to sell product, or have a favorable view in the market place. This is not a mandate from the government, but from non-governmental authoritative bodies. Failure to achieve the benefits from these projects would negatively impact and harm the company's brand image.
| 1.2.7 | New Technology or Functionality
The technology or functionality DOES NOT currently exist. Something new needs to be added at Cooper for the technology and/or functionality to be present. These projects introduce something new to the business that helps create a strategic market advantage, helps the business run more efficiently or improves the efficiency of an individual department or business function.
| 1.2.8 | Operational Mandated
A change is required to maintain sustainable and quality day-to-day operations in Operations. This can be a change to an existing process or a new process needed for the desired and proper functioning of Operations. Failure to deliver the project results may result in significant operational failure or major increases in operational costs. These are projects that are the migration of services and/or environments to ensure a current, stable operating environment. An example would be Lifecycle Management, Preventative Maintenance, Corrective Fixes and Infrastructure Projects.
| 1.2.9 | Revenue / Revenue Generation
Revenue is the income to the business from its normal business activities. Revenue Generation is the ability to generate revenue due to the realization of the project deliverables by additional revenue coming into the business by increasing top-line growth. These are the processes by which a company markets and sells a product or service to produce income. Revenue could be a potential benefit to Cooper from the project.
| 1.2.10 | Strategic Project
These projects help align the Company to achieve future revenue and/or benefits after project deliverables are implemented. For example, a strategic project could be putting systems in place to enable Cooper to sell to a new market.
| 1.2.11 | Technology Mandated
A project that is required to implement a change that is needed to support an upgrade or provides the foundation for future infrastructure needs or desired functionality. Failure to deliver the project results may result in the inability to sustain a current technology or to introduce a new technology resulting in a significant loss to the business.
2 | Form Instructions
2.1 | General Program / Project Information
| 2.1.1 | Complete header information for the project.
2.2 | Business Case
| 2.2.1 | Business Problem Identification - Describe the problem
Clearly and thoroughly describe the current situation. Note the business needs that are not being met or business requirement that need to be provided. Include a current process flow , where applicable.
| 2.2.2 | Business Description of Success
Clearly identify what is lacking with the current functionality and what functionality needs to be improved for success. This is not a statement of the customer's view of a solution (a potential answer to the problem), but rather what functionality or service that must be delivered by the project.
| 2.2.3 | What are the things included in this project? (IN SCOPE)
Clearly articulate what products, processes or services that are to be included in the project. This information should provide clear boundaries of what the project will deliver and should be stated in terms of deliverables.
| 2.2.4 | What are the things definitely not in this project? (OUT OF SCOPE)
Cleary articulate products, processes or services that will NOT be considered as part of this project. These are product, processes, or services that are not within the boundaries of the project. There are potential deliverables that will not be provided by the project.
| 2.2.5 | Are there required delivery dates for this project? If so, describe requirements below.
If there are deadlines, note those deadlines and business necessity/requirements for meeting those dates. Clearly state any penalties, income generation loss, etc. that would result if this date is not met.
| 2.2.6 | Explanation of the potential benefits to Cooper
Use this area to explain any potential benefits that Cooper will realize as a result of implementing the deliverables of this project.
2.3 | Project Benefit and Compliance Areas
| 2.3.1 | Describe how the project classification was established for selection of the category in this section. Utilize the definitions for the terms in the Business Case.
|  | 2.3.1.1 | Existing / Legacy Technology or Functionality Enhancements
Indicate the amount of potential gain in revenue per year after the project results are realized.
|  | 2.3.1.2 | New Technology or Functionality
Indicate the number of departments that will benefit from the results of the project. If applicable, indicate the amount of revenue per year.
|  | 2.3.1.3 | Operational Mandated
Indicate the loss or potential loss to the business if the results of the project are not realized.
|  | 2.3.1.4 | Technology Mandated
Indicate the loss or potential loss to the business if the results of the project are not realized.
|  | 2.3.1.5 | Continuous Improvement
Indicate the amount of improvement that could be made per year.
|  | 2.3.1.6 | Strategic Project
These projects help align the Company to achieve future revenue and/or benefits after project deliverables are implemented. For example, a strategic project could be putting systems in place to enable Cooper to sell to a new market.
|  | 2.3.1.7 | Government Mandated
If the mandate is not achieved, list the impact on the business.
|  | 2.3.1.8 | Industry Mandated
List the amount of potential loss the business will incur if the project results are not realized.
2.4 | Strategic Alignment
| 2.4.1 | This section is to measure the amount of project alignment to the 6x12x20 Strategic Priorities. (The Strategic Alignment tab where the current 6x12x20 can be copied fro the intranet and pasted to this tab for fast reference when filling out the Business Case)
2.5 | BIS Assessment
| Cells that are colored light yellow: |  |  | need to be completed as part of the Business Case and BIS Assessment.
| 2.7.1 | After interviewing the business customer to gather the information required for the completion of the Business Case document, there needs to be a high-level assessment of the resources required to deliver the project results. The BIS Assessment provided a worksheet to identify BIS resources to complete the project work as well as estimate the hours of effort and the project budget.
3 | Form Revisions
3.1 | When the form is changed for a new revision. This is done by modifying the revision number in the 3rd row on the BLANK - BIS Business Case.
[5 empty] | Business Owners | EA
[5 empty] | Brent Lovell | Curtis Farthing
[5 empty] | Jill Schroeder | Garry Chatman
[5 empty] | Jim Blevins | Kinjlak Kalia
Joe Creque
Judson Pitt
Kimberly Secord
Rodney Carlton
Todd Wilson
Tom Zepp
Van Husted

## Revision History (hidden)
Document Revision History:
Revision Number | Change | Date | Changed By
0 | Draft document | 2015-03-09 | JMS
1 | First document on Share Point | 2015-04-01 | CDS
2 | Modified document based on 5/1/15 meeting. Added metrics for Strategic Alignment. | 2015-05-05 | ATH
3 | Version 3 was added to BRM Share Point Site | 2015-05-12 | ATH
4 | Modified the Business Case to use drop-down lists. Added lines for the 1st and 2nd Prioritization Matrix that can be copied from the Business Case to the Prioritization matrix Document. Fixed errors in the BIS Assessment. | 2015-06-11 | ATH
5 | Incorporated changes from the 6/12/15 BRM / SDD Process Improvement Meeting into the BIS Project Cost Assessment. | 2015-06-16 | ATH
6 | Added "NA" to several categories as a selection criteria. Updated the Form Instructions page. Added the Security, BASIS and DATA Teams to the BIS PRJ Cost Assessment. Modified the "Total Project" summary and added an "AR Total Cost" to the BIS PRJ Cost Assessment tab. | 2015-07-08 | ATH
7 | Modified the definition of Continuous Improvement | 2015-07-09 | ATH
8 | Entered the "Work stream" in the "General Program / Project Information" section. Work stream was also added to the rows to copy to the Prioritization Matrix. | 2015-07-16 | ATH
9 | Removed the reference to "discretionary. Semi-discretionary and Non-discretionary". Updated the definitions in the Form Instructions tab including "Strategic Project". Changed the Strategic Project ranking criteria to include sense of urgency, benefit gain to Cooper and strategic alignment to the 6x12x20 on one measure. Added two rows to show the costs on the Business Case from the BIS PRJ Cost Assessment Sheet. Removed any ranking criteria that was not used in the "1st scoring" matrix. | 2015-08-17 | ATH
10 | No update for v10 of business case | ?? | RAC
11 | Created a new tab called Business Case Checklist which will be required for all future ideas to be submitted or approved for governance. | 2016-03-07 | RAC
12 | Corrected spelling errors and fixed revision issues | 2016-07-26 | RMS
DRAFT 13 | Deleted the old Roles and added the new Roles to match the new Roles in CA PPM (from the 9/7/16 meeting with the BRMs). Updated Mgr names and groups on the Business Case Checklist | 2016-10-17 | ATH
14 | Added Robin Kretzinger (Budget) for a review prior to Governance Meeting | 2017-02-28 | JAS
15 | Updated names in Checklist to reflect org changes, attrition and assign primary and back up for applicable areas. Also updated Architecture to reflect being Enterprise Architecture. | 2017-10-09 | RAC
16
17 | Version drafted to include new tab for CostBenefit per request from BIS PMO group. This version was merged with v18 changes and released under v18. | 2018-05-14 | RAC
18 | Updated Business case and Resource & Cost Assessment form to streamline usage, remove unused sections and to better segregate costs. Moved alignment portion from prior version to new tab called Alignment, added a new tab called Cost Benefit per request from BIS PMO and lastly added new tab called PMAP for Process Map attached to business case. | 2018-05-14 | RAC
19
20
21
22
23
24

## Business Case
Cooper Tire & Rubber Company
BIS Business Case
DRAFT Rev. 18, 05/02/2018
1. General Program / Project Information
IDEA #: | 6928 | IDEA Name: | Internation Certificate (ICS) upgrade/LCM |  | Work stream: | OPQ
Date Submitted: | xx/xx/xxxx | Business Sponsor: | Tom Zepp |  | Business Case Author | Tom Busch
2. Business Case
Business Problem Identification - Describe the problem
This system has been defined to close a gap between Marketing & Quality by identifying products that require international certifications by country prior to sale. ICS is the system of record for major certifications that Cooper holds for compliance of shipping product to international locations. The major certifications tracked through the system are E-mark (European Union), I-mark (Brazil), GSO (Gulf States Organization), CCC (China), & NOM (Mexico). International Certificate System (ICS) application was created in a 2005 dot net for the "Technical" database as a different schema in an Oracle 10 level. Quality needs this application and schema to be on a supported level of infrastructure.
Business Description of Success
ICS is upgraded to Visual Studio dot net 2013 framework version for application development in a Oracle 12c database, and the standard features still function as per HP-ALM Segment for ICS.
What are the things included in this project? (IN SCOPE)
** Upgrade ICS code to current standard for Visual Studio dot net 2013 framework for application development, or newest standard designation. ** Migrate ICS schema from "Technical" database to new "ICS" 12c Oracle db running Windows 2016 ** Remove any reference in ICS database procedures for materialized views in the BOM database in SKU_Master. These views were prior to OPQ.I.8265 interface and shall be removed from the code, as that data exist in SAP material master. ** Remove API call that has links into the TRACS schema on the Technical database (Oracle 10). The TRACS portion will be eliminated (it was originally to pull tire testing test results from TRACS, but now that all test data is in SAP, and they don’t need to go back further than what it is in SAP). This removal is considered as part of the upgrade. ** Re-point: (a) http://cooperwebfinprod/scit/applications/ICSWeb/home.aspx to the new oracle 12.2 database on server. (b) MMS (First Tire Out sheets - get the stamping information from a ICS view) - ICS links to the new oracle 12.2 database on server. (c) NPR - uses new product request for countries - uses ICS certification, stamping identification to the new oracle 12.2 database on server. ** DBA to determine if a new Oracle 12c database server is required to support this solution. If so, that will be added to the tasks and costs.
What are the things definitely not in this project? (OUT OF SCOPE)
Any other development not mentioned in the scope of this project.
Are there required delivery dates for this project? If so, describe requirements below
Explanation of the potential benefits to Cooper
Additional explanation of the costs to work the project (if necessary)
Oracle 12c database, Oracle 12c database server
From the BIS PRJ Cost Assessment Sheet
AR Project Total Cost (External, Expense and CapEx): |  |  |  |  | 2660
3. Other Information
Brief description of BIS needs if not included in the top portion of this document.
Describe in detail what is needed from BIS. Include applications.
Risk Identification
Describe in detail any known contingencies
Cross Functional Impact
Describe in detail any cross functional impact.
Additional comments about the project:
This may include assumptions relevant to the project that is being recommended.

## Resource & Cost Assessment
Cooper Tire & Rubber Company
BIS Project Cost Assessment
DRAFT Rev. 18, 05/02/2018
1. General Program / Project Information
IDEA #: | 6928 | IDEA Name: |  |  | Internation Certificate (ICS) upgrade/LCM | Work stream: | OPQ | Business Case Author: |  | Tom Busch
Date Submitted: | xx/xx/xxxx | Business Sponsor: |  |  | Tom Zepp |  |  |  |  | Tom Busch
Total Project Estimated Hours: | [9 empty] | 108
[9 empty] | Internal BIS Hours | 80
[9 empty] | PK Factory Sourced Hours | 28
[9 empty] | Accenture Factory Sourced Hours | 0
[9 empty] | HCL Factory Sourced Hours | 0
[9 empty] | AR Project Total Cost (External, Expense and CapEx): | 2660
Total Capital Investment Required? (Roles and Non Role): | [9 empty] | 2660
Total Expense or Lease Investment Required? | [9 empty] | 0
Estimated Effort by Role Required
Standard Internal BIS Resource Roles |  |  | Brief Description of Specific Work on this Project |  |  |  |  | Estimate Provided by |  | Effort Hours | Sourcing
Administrator - Network | [10 empty] | Accenture - non-Factory
Administrator - Security | [10 empty] | Accenture - Factory
Administrator - Server | [10 empty] | ProKarma - Factory
Administrator - Transition | [10 empty] | ProKarma - Non-Factory
Analyst Developer - BI, Data and EDI | [10 empty] | BIS Internal
Analyst Developer - Curing | [10 empty] | HCL
Analyst Developer - Finishing | [10 empty] | Other
Analyst Developer - LMAT
Architect
Business Analyst |  |  | Functional Design Document, communication, analysis,etc. |  |  |  |  | Tom Busch |  | 40
DBA - Oracle |  |  | DBA to create new Oracle 12c db; migrate ICS from Oracle 10 (Technology) to new Oracle 12c database; verify that JOB (OPQ.I.8265) to SAP is scheduled for new source. Determine if a new database server is required for solution |  |  |  |  | Curtis Farthing
DBA - SQL Server
Developer |  |  | Upgrade code to DOT Net standard (2013), and remove Tracs links, and materialized views; repoint incooper links, verify on-demand webservices still function |  |  |  |  | Chris Wolfe
Developer - Java
Factory Skills
Testing |  |  | UAT test coordination/testing activity |  |  |  |  | Tom Busch |  | 40
SAP
SAP - ABAP
SAP - Basis
SAP - MII
SAP - PI |  |  | Accenture PI - listed below |  |  |  |  | Chris Wolfe
SAP - Portal
SAP - Security
System Analyst Developer
Technician
Sub-Total (Standard BIS Resource Role Hours): | [9 empty] | 80
BIS Internal Project Lead |  |  |  | PL Hours (estimated at 35% of the overall project effort): | [5 empty] | 0
|  |  |  | Total Resource Hours (all roles): | [5 empty] | 80
Estimated Role Sourcing including non-BIS roles
Role |  |  | Sourcing (PK, AC, HCL, Int) | Required Skillsets/Named Resources if needed |  |  |  | Hours | Rate, $/Hr | Costs
Project Lead |  |  | ProKarma - Factory | Project Lead Cost |  |  |  | 28 | 95 | 2660
ProKarma Factory |  |  | ProKarma - Factory | Technical Lead - Oversight |  |  |  | 0 | 60 | 0
Accenture Factory |  |  | Accenture - Factory | SAP PI update OPQ.I.8265 interface links ICS inbound to SAP, and outbound from SAP to ICS. Verify that the flat file for PI is re-pointed to new ICS database/database server to update SAP functions in new environment. |  |  |  | 0 | 65 | 0
HCL Factory |  |  | HCL | Cost of new database and database server |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
Role | [7 empty] | 0 | 0 | 0
Role | [7 empty] | 0 | 0 | 0
Role | [7 empty] | 0 | 0 | 0
Total Cost: Resources : | [9 empty] | 2660
Non-Role Driven Project Costs - Captial
Identify any costs that would be required to support the project
Cost Description |  |  | Cost Type (Exp/Lease/Cap) | Specific Requirements (list any specific skills required) |  |  |  | Units | Cost/Each | Total Costs
Business Materials |  |  | Capital |  |  |  |  | 0 | 0 | 0
Software (including 1st year Maint) |  |  | Capital |  |  |  |  | 0 | 0 | 0
Software Development Labor |  |  | Capital |  |  |  |  | 0 | 0 | 0
<insert new row> |  |  | Capital |  |  |  |  | 0 | 0 | 0
<insert new row> |  |  | Capital |  |  |  |  | 0 | 0 | 0
Non-Role Driven Project Costs - Captial - Total | [8 empty] | 0 | 0
Non-Role Driven Project Costs - Expense or Lease
Identify any costs that would be required to support the project
Cost Description |  |  | Cost Type (Exp/Lease/Cap) | Specific Requirements (list any specific skills required) |  |  |  | Units | Cost/Each | Total Costs
Hardware (including 1st Year Maint) |  |  | Lease |  |  |  |  | 0 | 0 | 0
Services |  |  | Expense |  |  |  |  | 0 | 0 | 0
Taxes & Fees |  |  | Expense |  |  |  |  | 0 | 0 | 0
Travel Expenses |  |  | Expense |  |  |  |  | 0 | 0 | 0
<insert new row> | [7 empty] | 0 | 0 | 0
Non-Role Driven Project Costs - Expense or Lease - Total | [8 empty] | 0 | 0
Note on A19: This role manages the network making sure the computer hardware and network infrastructure are effectively maintained.
Note on A20: Non-SAP security role.
Note on A21: This role is responsible for the upkeep, configuration and reliable operation of servers.
Note on A22: This is a role of someone on the Transition Team who performs Redwood, ALM/Testing, Change Management Tasks.
Note on A23: This is a role that works with EDI, BI or is part of the Data team.
Note on A24: This is a role that is responsible for the support and development of various, non-specific systems and technology. This role has specialized knowledge of the curing environment.
Note on A25: This is a role that is responsible for the support and development of various, non-specific systems and technology. This role has specialized knowledge of the finishing environment.
Note on A26: This is a role that is responsible for the support and development of various, non-specific systems and technology. This role has specialized knowledge of the LMAT environment.
Note on A27: This role controls the structure and interfaces between all of the systems and the technologies used.
Note on A28: The role that works with the business that are gathering and documenting business case information and requirements for project charters. Not a specialist in any one area, but more of a generalist in many areas.
Note on A29: This is a role that works directs or performs all activities related to maintaining a successful Oracle database.
Note on A30: This is a role that works directs or performs all activities related to maintaining a successful SQL Server database environment.
Note on A31: This role is a Developer that supports and develops applications with tools in the Microsoft stack.
Note on A32: This role is a Developer that supports and develops applications with Java.
Note on A33: A role to track factory hour usage.
Note on A34: This is a role for those in Management. It is unlikely that this role will show up in a future Portfolio View as a role on projects.
Note on A35: This is the general role of those who work with SAP. Typically this is a System Analyst or configurator with focus in non-constrained work streams.
Note on A36: This role is a Developer that supports and develops applications with the SAP ABAP toolset.
Note on A37: This role is responsible for the upkeep, configuration, and reliable operation of the SAP infrastructure.
Note on A38: This is the role of those who work with SAP. Typically this is a System Analyst or configurator with focus in the constrained area of MII.
Note on A39: This is the role of those who work with SAP - specifically in the support and development of PI interfaces.
Note on A40: This is the role of those who work with SAP. Typically this is a System Analyst or configurator with focus in the constrained area of Portal.
Note on A41: This is the role of those who work with SAP - specifically in the support and development of Security.
Note on A42: This is a role that is responsible for the support and development of various, non-specific systems and technology.
Note on A43: This is a role that supports various client devices such as computers, phones, RF devices, etc.

## CostBenefit
Cooper Tire & Rubber Company
BIS Project Cost Assessment
Rev. 18, 05/02/2018
IDEA #: | 6928
IDEA Name: | Internation Certificate (ICS) upgrade/LCM
Overall Project Costs:
Funding: (Select one) | BIS-Budgeted | [6 empty] | BIS-Budgeted
Budget Line Item |  |  |  | **If BIS-Budgeted |  |  |  | BIS-Unbudgeted
| Capital | Expense | Total |  |  |  |  | Business Funded
One-time (Total) | 0 | 0 | 0
Internal |  |  | 0
External |  |  | 0
Annual (Total) |  | 0 | 0
Internal |  |  | 0
External |  |  | 0
TOTAL (Total) | 0 | 0 | 0
Internal (Total) | 0 | 0 | 0
External (Total) | 0 | 0 | 0
AR Estimate:
Estimated Benefits - Hard |  |  |  | Estimated Benefits - Soft (Efficiencies that cannot be taken to the bottom line)
| One-Time | Annual Benefits |  |  | One-Time | Annual Benefits | Description
Labor Savings |  |  |  | Labor Savings
Material Savings |  |  |  | Material Savings
Other Savings |  |  |  | Other -
Working Capital |  |  |  | Other -
Top Line Growth |  |  |  | Other -
Total | 0 | 0 |  | Total | 0 | 0
Annual Benefits Start: |  | <year>
One-Time Year in which Realized: |  | <year>
Payback (nbr years):
ROI:
NPV:
Note on B13: Indicate internal labor implementation costs that will be capitalized
Note on C13: Inidcate internal implementation costs that will be treated as expense and unable to capitalize such as data migration and planning
Note on B14: Indicate implementation costs to be spent with a third party that can be capitalized
Note on C14: Indicated implementation costs that will not be capitalized.
Note on C16: Indicate internal on-going costs such as new headcount to maintain and enhance a new capability
Note on C17: The on-going cost spent with a thrird party such as lease or maintenance.
Note on B28: This category of savings is rarely used. Consider the one-time cost avoidance a capability can generate
Note on C28: Annual labor savings are usually a result of head-count reductions
Note on B29: This category of savings is rarely used.
Note on C29: Indicate that on-going input or raw material costs
Note on C31: Usually comes in the form of inventory reduction, accounts receivable/days outstanding reduction, or favorable terms on payables.
Note on B32: Indicate the one-time increase in gross profit as a result of increased sales.
Note on C32: Indicate the on-going increase in gross profit as a result of increased sales.
Note on C35: What year do the annual savings begin?
Note on C36: What year will the on-time benefit hit?
Note on C37: Insert from Cashflow sheet provided from Finance.
Note on C38: Insert from Cashflow sheet provided by Finance.
Note on C39: Insert from Cashflow sheet provided by Finance.

## Alignment
1. Project Benefit and Compliance Areas
[9 empty] | Criteria |  |  | Selection from Drop Down List
Existing / Legacy Technology or Functionality Enhancements |  |  |  |  | Potential Gain (per year): |  |  | NA | Low (~$20k) | Medium ($50k to 100k) | High (>$200k) | Medium ($50k to 100k)
New Technology or Functionality |  |  |  |  | Potential Gain (per year): |  |  | NA | Low (~$100k) | Medium ($200k to 300k) | High (>$400k) | Medium ($200k to 300k)
Operational Mandated |  |  |  |  | Potential Loss (per year): |  |  | NA | Low (<$20k) | Medium ($20k to 50k) | High (>$50k) | High (>$50k)
Technology Mandated |  |  |  |  | Potential Loss (per year): |  |  | NA | Low (<$20k) | Medium ($20k to 50k) | High (>$50k) | Low (<$20k)
Continuous Improvement |  |  |  |  | Potential Gain (per year): |  |  | NA | Low (<$20k) | Medium ($30k to 60k) | High (>$100k) | Medium ($30k to 60k)
Strategic Project |  |  |  |  | Urgency / Benefits / Strategic Alignment: |  |  | NA | Moderate urgency, marginal benefits, At least (1) 6x12x20 category | High urgency, moderate benefits, At least (3) 6x12x20 categories | High urgency, significant benefits, At least (5) 6x12x20 categories | High urgency, significant benefits, At least (5) 6x12x20 categories
Government Mandated |  |  | Cost of Non-Compliance (per year): |  |  |  |  | NA | Low (<$20k) | Medium ($20k to 50k) | High (>$50k) | NA
[7 empty] | Extreme Legal Ramifications / Penalties if in Non-Compliance: | Yes / No |  |  |  | No
Industry Mandated | [6 empty] | Potential Loss (per year): | NA | Low (<$20k) | Medium ($20k to 50k) | High (>$50k) | Medium ($20k to 50k)
2. Strategic Alignment
Drive Topline Profitable Growth | [11 empty] | Select Yes or No from the Drop Down List
Americas | Generate unit volume demand in PCR replacement by optimizing product and channel mix | [6 empty] | Improves product range: |  |  |  | No
[8 empty] | Improves Channel Mix: |  |  |  | No
| Penetrate OE | [6 empty] | Increase OE Contracts: |  |  |  | No
| Secure supply and grow TBR | [6 empty] | Increases the amount of supply secured: |  |  |  | No
[8 empty] | Increases projected growth: |  |  |  | No
Asia | Generate unit volume demand in PCR replacement by strengthening distribution and focusing on Tier 2 and 3 "moon cities" | [6 empty] | Improves product range: |  |  |  | No
[8 empty] | Improves channel mix: |  |  |  | No
| Continue to penetrate OE | [6 empty] | Increases the number of OE Contracts: |  |  |  | No
[8 empty] | Increases revenue of OE Contracts: |  |  |  | No
| Secure supply and grow TBR | [6 empty] | Increases the amount of supply secured: |  |  |  | No
[8 empty] | Increases projected growth: |  |  |  | No
Europe | Generate unit volume demand in PCR replacement by: Penetrating core U.K. Market with the Cooper brand Growing in attractive markets like Germany, Russia and Middle East Emphasizing growth and niche products like racing and motorcycle | [6 empty] | Improves product range: |  |  |  | Yes
[8 empty] | Improves Channel Mix: |  |  |  | Yes
Develop a competitive cost structure and improve profitability | [11 empty] | Select Yes or No from the Drop Down List
Pursue globally competitive operations through: | Describe how the project would help Cooper achieve World-Class Manufacturing Capabilities. | [8 empty] | Improves world-class Mfg capabilities: |  | Yes
[10 empty] | Level of impact on world-class Mfg capabilities? |  | High
| Describe the Conversion Cost Reduction impact this project will have. | [8 empty] | Reduces conversion costs:
[10 empty] | Level of impact on conversion cost reduction? |  | High
| Describe how this project will Optimize Total Material Cost. | [8 empty] | Optimizes total material costs: |  | Yes
[10 empty] | Level of impact on material cost optimization? |  | Medium
Build organizational capabilities | [11 empty] | Select Yes or No from the Drop Down List
Build necessary global enablers and improve talent and leadership development: | Describe how this project will help improve IT / ERP. | [8 empty] | Improves IT / ERP: |  | Yes
| Describe how this project will help improve HR / Talent Development. | [8 empty] | Improves HR / Talent Development: |  | No
| Describe how this project will help improve LEAN Six Sigma. | [8 empty] | Improves LEAN Six Sigma: |  | No
| Describe how this project will help improve Cooper Production Systems. | [8 empty] | Improves Cooper Production Systems: |  | Yes
| Describe how this project will help improve Technical Capabilities. | [8 empty] | Improves Technical capabilities: |  | No
Rows to Copy and Paste in the Prioritization Matrix Below Here:
1st prioritization matrix Information:
|  | (Copy the light green |  | cells. Paste as values only)
[5 empty] | Work stream | Existing / Legacy Technology or Functionality Enhancements | New Technology or Functionality | Operational Mandated | Technology Mandated | Continuous Improvement | Strategic Project | Government Mandated | Industry Mandated
| _Potential Loss (per year): |  |  |  | 3 | 3 | 9 | 9 | 9 | 9 | 9 | 9 | 9

## Checklist
Last Updated: 8/10/2018
Step Number | Verification Group | Group Manager / Contact | Step Description | Person Spoken to? | Completion (Y, N, N/A) | Status | Comments (if needed)
1 | Operations | Judson Pitt | Server Team Review |  | x
1. Hours needed?
a. Internal
b. Factory
c. Staff Aug
2. Server capacity
3. Licensing needs
|  | Judson Pitt | BASIS Team Review
1. Hours needed?
a. Internal
b. Factory
|  | Jonna Shaffer | Licensing Review | email response | N/A | no involvement needed | 4/15/19 @12:54
a. SAP
b. BI
c. Etc.
|  | Jim Blevins | Security Team Review
1. Hours needed?
a. Internal
b. Factory
1. Cloud security concerns?
2. Specific data security concerns?
3. Internet/email security concerns
|  | Nick Schroeder | Network Team Needs? | email response | N/A | no involvement needed | 4/15/19 @12:26
Hours Needed?
|  | Chris Fleck | Service Desk and Desktop Needs? |  | x
Hours Needed?
2 | EIM | Curtis Farthing | Database Team Review |  | x
1. Hours needed?
a. Internal
b. Factory
1. Database Server/Hardware needs
2. Licensing needs
|  | AJ Tipton | Data Team Hours? | email response | N/A | no involvement needed | 4/15/19 @ 12:58
1. Hours needed?
|  | Christoph Egel | BI / Reporting Hours?
3 | EAD | Randy Wanamaker | OTC & SCM Development Team Review | email response | N/A | no involvement needed | 4/15/19 @ 1:40
1. Hours needed?
a. Internal
b. Factory
|  | Randy Wanamaker | FIN & HTR & PTP Development Team Review |  | x
1. Hours needed?
a. Internal
b. Factory
|  | Chris Wolfe | OPQ & RTP Development Team Review |  | x
1. Hours needed?
a. Internal
b. Factory
4 | EA | Joe Creque | Enterprise Architecture |  | x
|  | Kinklak Kalia | Application Architecture?
|  | Garry Chatman | BASIS Architecture?
|  | Van Husted | Infrastructure Architecture |  | x
5 | Internal Controls | Business Owner | Audit/Internal Controls Review
|  |  | 1. Do the proposed process modifications change the performance of existing controls or introduce new risks? |  | If Yes, then Internal Controls should be added as a Stakeholder on Project Charter |  | If unsure, the business owner should review the Internal Controls Framework (ICF) at http://incoopernew/sites/Finance/InternalControls/SharedDocuments/Internal%20Control%20Framework/Corporate/Corporate%20ICF%202016.xlsx link. If still unsure, business owner should contact Mariann Przysiecki, Global Internal Controls Manager. ")
2. Outside contractor concerns (RGOC)
6 | Purchasing | Michelle Cameron | Purchasing Review
7 | IT/Budget | Gina Shoemaker | Review of project from a Funding perspective |  | x |  | BIS funded LCM

## Notes
IDEA6928 - ICS | Business Case Notes
Project Document Revision 0
Last Updated MM/DD/YY
ID | Notes | REQ | Responsible Party | Verified By:
1 | ICS = International Certificate System |  |  |  | Inputs
2 | Dot Net application built in "Technical" database with a separate schema at 2005 level |  |  |  | SAP > ICS
3 | Technical db is Oracle 10 level |  |  |  | ICS > update Z-tables for sales
4 | ?? Would like to go to Oracle 12c if possible, that might only happen if migrate the db schema to another separate db or a new Technical db? |  |  |  | interface 8265
5 | Need to check with Jill S if Technical db activity?? |  | Jill Schroeder |  | Asynchronous (only initiates the operation) - update table ZOTCSO_PROD CERT
6 | Purpose : origonal need was a place to assign different Country certification identifies for each finished SKU/Tire. |  |  |  | Synchronous (blocks a process till the operation completes) - pulls from SAP
7 | Reports need revising? In Crystal Reports - if so what reports>
8 | update and make better if not too much time/cost |  |  |  | CMDR - SAP for inputs for ICS
9 | Quality Dept Mario Martin - super user |  |  |  | FA0017 - Technical db and views from CMDR
10 | Locate in Tech building left off main hallway before take doorway to Curtis
11 | UI was created to show data that was pulled from SAP
12 | Job runs at night looking for a change in Ztables (which ones?)
13 | when receive a customer order, in a country that does not have the Country - Certificate - SKU combination, the order will be put on "Blocked Order"
14
15 | Check |  |  |  | Notes form Jill Seitz
16 | Webserveres |  |  |  | FA0092 - Production Server
17 | database layer servers |  |  |  | FA0091 - QA
18 | business layer servers |  |  |  | FA0090 - Development
19 | database (Technical)
20 | SAP interface |  |  |  | Corporate web server - is being updated to Framework - 4.0 or 4.5
21 | Jobs that run and when
22 | Oracle db level 11g or 12c
23 | migrate schema to another Oracle 12c environment
24 | Report changes |  | None found
25 | SNOW requests |  | None found
26 | Look at the incidents to get an idea of which requests should be a priority |  | None found
27 | look at SDR in Sharepoint
28
Chris Wolfe | On this side of the street, we are using .Net 2013 for application development.
ICS database does have procedures pointing to materialized views in the BOM database in SKU_Master so upgrading to 11.2.0.4 is preferred. There’s the possibility these procedures could be rewritten as part of the project if we really want to move to Oracle 12.
Curtis, are there any Oracle 12 databases for our custom developed applications yet? Not yet…
Also, there is an API that gets called that has links into the TRACS schema on the Technical database (Oracle 10). At this point, the TRACS portion could be eliminated (it was originally to pull tire testing test results from TRACS, but now that all test data is in SAP, and they don’t need to go back further than what it is in SAP). So this probably needs to be considered as part of the upgrade.
Curtis Farthing | The standard for Oracle databases is version 12.2 or higher running on Windows 2016. The only exception would be applications that need database links back to Oracle 9i; in which case we would use Oracle 11g running on Windows 2012.
Jill Schroeder | Technology database - new one started at the Oracle 11g level
|  | 11.2.0.4 | Oracle 11g support through December 2020
https://apex.oracle.com/database-features/
19c
18c
|  | 12.2.0.1 | 12c releae 2
|  | 12.1 | 12c realease 1 | 2019-07-01
|  | 11.2.0.4 | 11g releae 2
Custom Z-tables in SAP
ZOTCSO_CERTREO | is a certification required
ZOTCSO_CERTTYPE | what type of certifcation is needed
ZOTCSO_PRODCERT | what product it relates to

## Assumptions (hidden)
#VALUE! |  | Business Case Assumptions |  |  | PRJXXXX - Project Name |  | Business Case Notes and Options
Project Document Revision 0 |  |  |  |  | Project Document Revision 0
| Last Updated MM/DD/YY |  |  |  |  | Last Updated MM/DD/YY
ID | Assumption | Responsible Party | Verified By: | Hierarchy | ID | Note/Comments | Responsible Party | Verified By: | Comments
1 |  |  |  |  | 1
2 |  |  |  |  | 2
3 |  |  |  |  | 3
4 |  |  |  |  | 4
5 |  |  |  |  | 5
6 |  |  |  |  | 6
7 |  |  |  |  | 7
8 |  |  |  |  | 8
9 |  |  |  |  | 9
10 |  |  |  |  | 10
11 |  |  |  |  | 11
12 |  |  |  |  | 12
13 |  |  |  |  | 13
14 |  |  |  |  | 14
15 |  |  |  |  | 15
16 |  |  |  |  | 16
17 |  |  |  |  | 17
18 |  |  |  |  | 18
19 |  |  |  |  | 19
20 |  |  |  |  | 20
21 |  |  |  |  | 21
22 |  |  |  |  | 22
23 |  |  |  |  | 23
24 |  |  |  |  | 24
25 |  |  |  |  | 25

## Make Hay (hidden)
Equipment Information
1 | Categories
1.1 |  | Class: Quadruplex extruder vs Triplex extruder
1.2 |  | Manufacturer: HF
2 | Locations (Mill Room)
2.1 |  | Systems: (XTRDR011) or (XTRDR008)
2.1 |  |  | Positions: Cooling Zones 1 on Second floor (Floor-02)
2.2 |  |  | Assets: Cooling Zone 1 Blow-off motor
3 | Closing Codes - Types
3.1 |  | Action codes - steps necessary to correct the problem
3.2 |  | Cause codes - root casue of the problem
3.3 |  | Failure codes - Reason for the failed equipment
3.4 |  | Problem codes - observed equipment failure - a leak or overheating
Departments
Meter
Duration
Criticality code
Equipment Profiles
Templates for different types
Asset numbers
Serial numbers
manufacturer

## tests (hidden)
td://test_cooper.default.fa0438:8080/qcbin/[AnyModule]?EntityType=ITest&EntityID=15366&ALL_ENTITY_IDS=15366,15365,15370,15369,15368,15367,15362,15363,15364,15390,15392,15395,15394,15393,15389,15400,15401,15409,15410,15402,15403,15413,15414,15411,15412,15404,15397,15398,15399,15405,15407,15408,15406,15396,15391,15354,15356,15358,15360,15355,15357,15359,15361,15375,15374,15379,15378,28076,15377,15376,15371,15372,15373,15384,15383,15388,15387,15386,15385,15380,15381,15382,16162,16161